## Sheet2
Week # | 1 |  |  |  |  | 2 |  |  |  |  | 3 |  |  |  |  | 4 |  |  |  |  | 5 |  |  |  |  | 6 |  |  |  |  | 7 |  |  |  |  | 8 |  |  |  |  | 9 |  |  |  |  | 10 |  |  |  |  | 11 |  |  |  |  | 12 |  |  |  |  | 13 |  |  |  |  | 14 |  |  |  |  | 15 |  |  |  |  | 16 |  |  |  |  | 17 |  |  |  |  | 18 |  |  |  |  | 19 |  |  |  |  | 20
Task | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F
Intro to main assignment
Intro to side assignment
Meeting With client
GUI tasks
Design dashboard GUI by sketch
Implement dashboard GUI
Functionality of dashboard
Test GUI functionalities
Implement HeatMap on Dashboard
Test response to HeatMap
Displaying Tables on Dashboard
Displaying graphs on dashboard
Implementation of Javascript DataTable
Database tasks:
Creating Database
Populate database
Link database to GUI
Update database
Lit study:
Research on Excisting Dashboard
Research on Heatmap
Dashboard database
Angula.js
HTML
CSS
PHP
Javascript
Jquery.js
Bootstrap
Heatmap
Twitter plugin
Moving Widgets for dashboard
Research on Database (side pro)
Research on coupling structured/unstructured data
Types of graphs to display onto the dashboard
Project Documents to be written:
Draft project plan
Final Project Plan
Draft Planning
Write Report for project
Update Final report
Internship Supervisor visit
Weekly Log to Supervisor
Final Project Report
Company Presentation
Assessment meeting
Note on B1: Week 1 - Introduction to employees of MM Guide. - Introduction Main assignment - Introduction to second part of the main assignment. - Research on existing Dashboard provided the MM Guide company (Code review).
Note on G1: Week 2 Task During week: - Introduction to the side project. - Research on Heatmaps and google plugins (Twitter plug). - Research on different Javascript frame work (Angula, JQuery). - Write draft project plan. Progress 26% - Design dashboard GUI. Progress 35% - Implementation of GUI. Prgoress 25% Task for following week: - Improve on implementation of dashboard GUI design. - Update draft project plan. - Implement heatmap on dashboard GUI - Research Database (client side).
Note on L1: Week # Task during week: - update project plan. Progress 48% - Improve on smart dashboard GUI design. Progress 38% -Creating header: Progress 100% -Sider bar: Progress 25% (toggle for side bar giving issues) -Creating main content area to display graphs: Progress 10% - Implement Heatmap on smart dashboard GUI. Progress 35% -Test layout for heatmap on current dashboard: progress 25% - Prepration for up coming Meeting with Supervisors. Tash for following week: - Conduct the meeting between the supervisors and myself (trainee). - Research heatmap furthur. - Research on creating a database for the dashboard. - Link the dashboard to the database. - Update project plan base on points discussed in the meeting. - Research Database information.
Note on Q1: Week 4 Task during week: - Conduct scheduled meeting between supervisors and myself (trainee) - Write minute taken during supervisors meeting. - Update draft project plan. Progress 65% - Conduct research on Database for the project. Progress 85% - Design Database by sketch: Progress 65% -What type of database to use: Progress 100% (using MySql) -Creating tables for database: Progress 45% -Populate the database: Progress 25% - Testing functionality of the dashboard GUI - Link database to dashboard: Progress 75% - Connect dashboard to database: Progress: 25% - test connection to dashboard: Progress 25% - display list of tables to dashboard: Progress 25% Task for following week: - Test the functionalities of the dashboard and database further. - Print out tables with data to dashboard. - Research on implement the coupling between the structured data and unstructured data. - Research on automating the suggestive widgets to be embedded into the dashboard. After discusion: - Heatmap will not be implemented no longer. The use of it is not needed for this project. - Use a Bootstrap template for the GUI of the dashboard.
Note on V1: Week 5 Task during week: - Test the functionalities of the dashboard and database further. - Print out tables with data to dashboard. Progress 35% - Printing individual Tables with infor 25% -Populate the database: Progress 45% - Research on implement the coupling between the structured data and unstructured data. - Research on automating the suggestive widgets to be embedded into the dashboard. - Update Project plan to Final Project plan. Task for following week: due to the fact that I was sick for this week I still have to capitalize on the tasks that i have to focus on for this week onto next week.
Note on AA1: Week 6 Task during week: - Populating the database: Progress 75% - Improve on dashboard functionalities: Progress 50% - Switching to different pages on GUI: Progress 20% - Display of tables with info from the database: Progress 20% -How to use Javascript for dataTable: 10% -Write Intro to Main report: Progress 10% -Research on implementing Coupling between dashboard and unstuctured data. implementing couplig: Progress 20% Task for following week: - Update Report -Update Planning for Project -Improve on the display of the tables -implement graphs to the dashboard GUI -Update database -improve on implementing coupling
Note on AF1: Week 7 Task during week: - Update Report: Progress 10% -Update Planning for Project 35% -Improve on the display of the tables -Make table sortable and clean: Progress 20% -implement graphs to the dashboard GUI -Get info from tables: Progress0% -Updatable page so responsive to change of data: Progress 0% -Update database -Populate tables: Progress 75% -improve on implementing coupling Task for following week:
Note on AK1: Week 8 Task during week: Task for following week
Note on AP1: Week 9 Task during week: Task for following week:
Note on AU1: MEM (Hogeschool INHolland Haarlem):
Note on AZ1: MEM (Hogeschool INHolland Haarlem):
Note on BE1: MEM (Hogeschool INHolland Haarlem):
Note on BJ1: MEM (Hogeschool INHolland Haarlem):
Note on BO1: MEM (Hogeschool INHolland Haarlem):
Note on BT1: MEM (Hogeschool INHolland Haarlem):
Note on BY1: MEM (Hogeschool INHolland Haarlem):
Note on CD1: MEM (Hogeschool INHolland Haarlem):
Note on CI1: MEM (Hogeschool INHolland Haarlem):
Note on CN1: MEM (Hogeschool INHolland Haarlem):
Note on CS1: MEM (Hogeschool INHolland Haarlem):

## Sheet1
Week # |  | 1 |  |  |  |  | 2 |  |  |  |  | 3 |  |  |  |  | 4 |  |  |  |  | 5 |  |  |  |  | 6 |  |  |  |  | 7 |  |  |  |  | 8 |  |  |  |  | 9 |  |  |  |  | 10 |  |  |  |  | 11 |  |  |  |  | 12 |  |  |  |  | 13 |  |  |  |  | 14 |  |  |  |  | 15 |  |  |  |  | 16 |  |  |  |  | 17 |  |  |  |  | 18 |  |  |  |  | 19 |  |  |  |  | 20
Week days |  | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F
Task | Progress: %
Dashboard
Design GUI by sketch | 100 | bar: 1 M to 1 T
Implement GUI design | 100 | bar: 2 M to 3 F
Dashboard 0.1 | 100 | bar: 9 T to 9 F
Update Dashboard 0.1 | 100 | bar: 11 M to 11 W
Dashboard testing | 100 | bar: 12 M to 12 F; 17 T to 18 M
Fully functioning dashboard | 95 | bar: 14 W
Coupling
Design database | 100 | bar: 4 M to 4 W
Update design to database | 100 | bar: 6 M; 7 M; 7 T
Creatation of database | 100 | bar: 4 W to 4 F; 6 M; 6 T to 6 F
Populate database | 100 | bar: 5 M to 5 T; 6 T; 6 T to 6 F; 7 W
Link database to dashboard | 100
link to twitter plugin (excel) | 100 | bar: 7 M to 7 F
Display unsturcture data as graphs on Smart dashboard | 100 | bar: 7 T to 8 W
Functionality
Heat map implementation | No longer in use | bar: 3 W to 4 T
Display info from database (in the form of tables) | 100 | bar: 5 F to 6 T
Display graphs from twitter info | 100 | bar: 7 F to 8 W; 9 M to 9 W; 13 T to 13 T
menotring users | 100 | bar: 9 M to 9 F
Move Div/ Widgets | 100 | bar: 10 M to 10 F; 14 M to 14 W
Combin User interaction & widgets | 100 | bar: 11 M to 11 W; 12 M to 13 M
Future Possible functions:
Draggable widgets | 100 | bar: 10 M to 10 F; 16 W to 16 F
Job responsibilities
Meeting with Job supervisor | bar: 1 M to 1 T; 1 F to 2 T; 2 T to 3 T; 3 F to 4 W; 5 M to 5 T; 6 M; 6 T to 7 T; 7 F; 8 T; 8 F to 9 M; 20 T
Presentation at Job | bar: 15 M to 16 M; 20 T
Companyy assesment | bar: 19 M
Documents: | 100 | bar: 1 M to 2 F; 4 M; 5 M
Draft Project Plan | 100 | bar: 5 M; 9 T to 9 F
Final Project plan | 100 | bar: 9 W
Planning | 80 | bar: 1 T to 1 F; 20 F
Draft report | 35 | bar: 6 T to 6 W; 7 W to 7 T; 13 M to 13 F
Final Report | 10 | bar: 14 T to 14 F; 20 F
Note on Q6: Decided to use dashboard template